## Overview
Radius Transport Management System
This is an Intelligent Information Management System for tracking assets maintenance, spares and service tracking, jobs monitoring, store inventory management and fuel record tracking with high real time data accuracy
| Tech | Cloud, Machine learining AI
| Stack | Nextjs
| Modules | Assets, Jobs, Fuel, Store
| Ver. | 0.0159
| Author | Joseph Mwadime
| 24% |  | 76%
| ID/Task | Module | Ice Box | In progress | Complete | Testing
| 1 | Assets | 1 | 1 | 0 | 1 | 1 | 0
| 2 | Dashboard | 1 | 1 | 0 | 1 | 0 | 1
| 3 | Users | 1 | 1 | 0 | 1 | 0 | 0
| 4 | Jobs | 1 | 1 | 0 | 0 | 1 | 0
| 5 | Fuel | 1 | 1 | 0 | 0 | 1 | 0
| 6 | Store | 1 | 1 | 0 | 0 | 1 | 0
| 7 | Report | 0 | 0 | 0 | 0 | 0 | 0
| 8 | Database | 0 | 0 | 0 | 0 | 0 | 0
| 9 | Training | 0 | 1 | 0 | 0 | 0 | 0
| 10 | Go Live | 0 | 0 | 0 | 0 | 0 | 0

## RIDDT
Rapid Implementation Development Design Test
User stories 2 features
| ID | Module | User | Story | Dev Remarks | Status | Progress | Test | Pending Build
| 1 | Users | Admin | Log in using username & password | ok | 1 | Done | Done | 0
| 2 | Users | Admin | Reset password option/s |  | 0 | to start | to start | 0
| 3 | Users | Admin | Access user system information & account notifications |  | 0 | to start | to start | 1
| 4 | Dashboard | Admin | View fuel overview, main tank/s level out & in fuel and volume used per frequency daily/weekly. | ok | 1 | Done | Done | 1
| 5 | Dashboard | Admin | View Jobs overview with jobs; completed, in progess, available mechanics, breakdowns, yard current capacity. | ok | 1 | Done | Done | 1
| 6 | Dashboard | Admin | show total spares in stock, reorder, frequency issues, rejected orders, frequency total costs. | ok | 1 | Done | Done | 0
| 7 | Dashboard | Admin | show active assests, under maintenance, service schedule. |  | 1 | Done | Done | 0
| 8 | Dashboard | Admin | show visualization of Assests vs cost, breakdowns,spares |  | 0 | to start | to start | 0
| 9 | Dashboard | Admin | show reports |  | 0 | to start | to start | 0
| 10 | Assets | Admin | create new asset and its details | ok | 1 | Done | Done | 0
| 11 | Assets | Admin | show all assets ? search |  | 1 | Done | Done | 1
| 12 | Assets | Admin | update assets info details |  | 0 | to start | to start | 0
| 13 | Assets | Admin | delete asset |  | 0 | to start | to start | 0
| 14 | Assets | Admin | add or update asset's oparator/driver |  | 0 | to start | to start | 0
| 15 | Assets | Admin | show sensor installed |  | 0 | to start | to start | 0
| 16 | Assets | Admin | Track and show assest service history |  | 0 | to start | to start | 0
| 17 | Assets | Admin | Plan assest for fleet and personalize communication with drivers |  | 0 | to start | to start | 0
| 18 | Assets | Admin | show each assest all history,service,spares & fuel |  | 1 | Done | Done | 0
| 19 | Jobs | Admin | show job overview status |  | 1 | Done | Done | 1
| 20 | Jobs | Admin | able to add new job and show it on the queue |  | 1 | Done | Done | 1
| 21 | Jobs | Admin | able to view queue and add more details on job items |  | 0 | to start | to start | 0
| 22 | Jobs | Admin | notify driver on state of the asset job item |  | 0 | to start | to start | 0
| 23 | Fuel | Admin | Issue fuel to assets with trip and reason |  | 1 | Done | Done | 0
| 24 | Fuel | Admin | get report of assets fueled at any time range |  | 0 | to start | to start | 0
| 25 | Fuel | Admin | add and calibrate fuel tank/s |  | 0 | to start | to start | 0
| 26 | Fuel | Admin | recieve & request fuel from tankers/distributer parties |  | 0 | to start | to start | 0
| 27 | Fuel | Admin | indicate fuel top ups deductable from assets operator/driver |  | 0 | to start | to start | 0
| 28 | Store | Admin | show inventory, be able to perform stock adjustments |  | 0 | to start | to start | 0
| 29 | Store | Admin | access to job active queue and issue requested or add spares |  | 0 | to start | to start | 0
| 30 | Store | Admin | prepair and place stock orders |  | 0 | to start | to start | 0
| 31 | Store | Admin | accept new location issues |  | 0 | to start | to start | 0
| 32 | Store | Admin | add or update spare information |  | 0 | to start | to start | 0
| 33 |  |  |  |  | 1 | Done | Done | 1
| 34 |  |  |  |  | 1 | Done | Done | 1
| 35 |  |  |  |  | 1 | Done | Done | 1

## Data
Data Points For System Use & Monitoring
no. | module | data | key | data type | length
1 | sign | username |  | text
|  | password |  | password
|  | user_id | pk | number
|  | organization |  | text
|  | role |  | text
|  | name |  | text
|  | email |  | email address
2 | assets | asset_id | pk | number
|  | registration | unique | text
|  | trailer_reg | unique | text
|  | model |  | text
|  | make |  | text
|  | fuel_capacity |  | number
|  | camera |  | text
|  | tracker |  | text
|  | fuel_sensor |  | text
|  | color |  | text
|  | type |  | text
|  | driver_id | fk | number
3 | drivers | driver_id | pk | number
|  | asset_id | fk | number
|  | driver_name |  | text
|  | contact |  | number
|  | email |  | email address
|  | age |  | number
4 | spare | spare_id | pk | number
|  | pid | unique | text
|  | name |  | text
|  | description |  | text
|  | units |  | text
|  | price |  | number
5 | fuel | issue_id | pk | number
|  | timestamp | unique | time
|  | user_id | fk | number
|  | fuel_id | fk | number
|  | asset_id | fk | number
|  | volume_issued |  | number
|  | remarks |  | text
|  | top_up_fuel |  | text
6 | jobs | job_id | pk | number
|  | timestamp | unique | time
|  | asset_id | fk | number
|  | job_number | auto@add | text
|  | requisition_no |  | number
|  | status |  | text
|  | description |  | text
|  | mechanics |  | text
|  | spare_id | fk | number
|  | quantity |  | number
|  | cost |  | number
7 | locations | location_id | pk | number
|  | name |  | text
|  | capacity |  | number
|  | lon |  | text
|  | lat |  | text
|  | description |  | text
8 | store_issue | issue_id | auto@add | number
|  | timestamp | pk | time
|  | asset_id |  | number
|  | job_id |  | number
|  | spare_id |  | number
|  | quantity |  | number
|  | status |  | text
|  | requester |  | text
9 | purchase_order | purchase_order_id | auto@add | number
|  | timestamp | pk | time
|  | supplier_id |  | number
|  | spare_id |  | number
|  | quantity |  | number
|  | delivery_date |  | time
|  | urgent |  | text
|  | cost |  | number
|  | status |  | text
10 | accept_order | accept_id | pk | number
|  | purchase_order_id | fk | number
|  | timestamp |  | time
|  | spare_id |  | number
|  | quantity |  | number
|  | price |  | number
|  | delivery_date |  | time
|  | urgent |  | text
|  | status |  | text
11 | suppliers | supplier_id | pk | number
|  | name |  | text
|  | type |  | text | 16 | fuel,spare,service
|  | description |  | text
|  | contact |  | number
|  | email |  | email address
12 | fuel_tanks | storage_id | pk | number
|  | fuel_id | fk | number
|  | name |  | text
|  | capacity |  | number
13 | fuel_order | fuel_order_id | pk | number
|  | supplier_id | fk | number
|  | fuel_id | fk | number
|  | volume_ordered |  | number
|  | delivery_date |  | time
remarks
|  | urgent |  | text
|  | status |  | text
14 | fuel_types | fuel_id | pk | number
|  | name |  | text
|  | description |  | text
|  | units |  | text
|  | unit_price |  | number
15 | users | work_id
name
position_id
phone
email
age
16 | positions | position_id
title
description
17 | service | service_id
asset_id
odometer
date
description
cost
|  | air_cleaner |  |  |  | 0,0 = not checked & not changed
|  | air_filter |  |  |  | 1,0 = checked & not changed
|  | engine_oil |  |  |  | 0,1 = not checked & changed
|  | coolant |  |  |  | 1,1 = checked & changed
gearbox_oil
gearbox
engine

## Cost
Implementation Cost
Package upto 500 assets
Initial cost |  | 1 month | 3 months | 6 months | 1 year
Cloud |  | 10000 | 25000 | 40000 | 80000
Licence |  | 12000 | 36000 | 70000 | 140000
Dev support |  | 15000 | 45000 | 90000 | 180000
| sub | 37000 | 106000 | 200000 | 400000
save 44,000/- on 12 months package
Operational cost
SMSs & alerts |  | 4500 | 13500 | 27000 | 54000
3rd part API |  | 1250 | 3750 | 7500 | 15000
Miscellaneous |  | 8550 | 25650 | 51300 | 102600
|  | 0 | 0 | 0 | 0
| grand | 51300 | 148900 | 285800 | 571600
*Highlighted cells should have computed formula